## Dashboard
Row Labels | Sum of Story Points
Sprint 1 | 13
Sprint 2 | 18
Sprint 3 | 19
Sprint 4 | 24
Sprint 5 | 18
Sprint 6 | 24
Sprint 7 | 18
Sprint 8 | 24
Grand Total | 158
Row Labels | Average of Cycle Time
Sprint 1 | 2.75
Sprint 2 | 4
Sprint 3 | 4.5
Sprint 4 | 5.75
Sprint 5 | 4.25
Sprint 6 | 6
Sprint 7 | 4.75
Sprint 8 | 3.75
Grand Total | 4.4688
Row Labels | Sum of Story Points | Average Velocity
Sprint 1 | 13 | 19.75
Sprint 2 | 18 | 37.875
Sprint 3 | 19 | 40.7143
Sprint 4 | 24 | 44.3333
Sprint 5 | 18 | 48.4
Sprint 6 | 24 | 56
Sprint 7 | 18 | 66.6667
Sprint 8 | 24 | 91
Grand Total | 158 | 158
Row Labels | Average of Cycle Time
Sprint 1 | 2.75
Sprint 2 | 4
Sprint 3 | 4.5
Sprint 4 | 5.75
Sprint 5 | 4.25
Sprint 6 | 6
Sprint 7 | 4.75
Sprint 8 | 3.75
Grand Total | 4.4688
Row Labels | Count of Task ID
Sprint 1 | 4
Sprint 2 | 4
Sprint 3 | 4
Sprint 4 | 4
Sprint 5 | 4
Sprint 6 | 4
Sprint 7 | 4
Sprint 8 | 4
(blank)
Grand Total | 32
Row Labels | Count of Task ID
Sprint 1 | 4
Sprint 2 | 4
Sprint 3 | 4
Sprint 4 | 4
Sprint 5 | 4
Sprint 6 | 4
Sprint 7 | 4
Sprint 8 | 4
Grand Total | 32

## Burndown -sprint 1
Day | Ideal -Pending work | Actual -Pending work | Completed Today
1 | 19 | 19 | 0
2 | 16 | 19 | 0
3 | 13 | 17 | 2
4 | 10 | 14 | 3
5 | 7 | 10 | 4
6 | 3 | 4 | 6
7 | 0 | 0 | 4

## Agile Performance Dashboard
Agile Sprint Performance Dashboard
Key Insights
Sprint velocity fluctuates across sprints, indicating variation in task complexity
Cycle time shows inconsistency, suggesting uneven workflow efficiency
Throughput remains stable, indicating consistent team capacity
Burndown shows delayed progress early in sprint and faster completion later
Overall delivery is stable but not evenly distributed across sprint days

## Raw data
Sprint | Task ID | Issue Type | Summary | Story Points | Status | Start Date | End Date | Assignee | Cycle Time
Sprint 1 | T1 | Story | Update braking guidelines | 3 | Done | 2025-01-02 | 2025-01-04 | You | 2
Sprint 1 | T2 | Story | Revise safety section | 5 | Done | 2025-01-02 | 2025-01-06 | Teammate A | 4
Sprint 1 | T3 | Task | Format document layout | 2 | Done | 2025-01-03 | 2025-01-05 | You | 2
Sprint 1 | T4 | Bug | Fix content errors | 3 | Done | 2025-01-04 | 2025-01-07 | Teammate B | 3
Sprint 2 | T5 | Story | Update driver instructions | 5 | Done | 2025-01-16 | 2025-01-20 | You | 4
Sprint 2 | T6 | Story | Add new compliance rules | 8 | Done | 2025-01-16 | 2025-01-22 | Teammate A | 6
Sprint 2 | T7 | Task | Review formatting | 3 | Done | 2025-01-17 | 2025-01-21 | Teammate B | 4
Sprint 2 | T8 | Bug | Fix grammar issues | 2 | Done | 2025-01-18 | 2025-01-20 | You | 2
Sprint 3 | T9 | Story | Revise emergency procedures | 8 | Done | 2025-01-30 | 2025-02-05 | Teammate A | 6
Sprint 3 | T10 | Task | Content formatting | 3 | Done | 2025-01-30 | 2025-02-02 | You | 3
Sprint 3 | T11 | Story | Update safety visuals | 5 | Done | 2025-01-31 | 2025-02-06 | Teammate B | 6
Sprint 3 | T12 | Bug | Fix inconsistencies | 3 | Done | 2025-02-01 | 2025-02-04 | You | 3
Sprint 4 | T13 | Story | Add new regulations | 8 | Done | 2025-02-13 | 2025-02-20 | Teammate A | 7
Sprint 4 | T14 | Task | Review handbook draft | 5 | Done | 2025-02-13 | 2025-02-18 | You | 5
Sprint 4 | T15 | Bug | Fix formatting issues | 3 | Done | 2025-02-14 | 2025-02-19 | Teammate B | 5
Sprint 4 | T16 | Story | Update diagrams | 8 | Done | 2025-02-15 | 2025-02-21 | You | 6
Sprint 5 | T17 | Story | Revise fuel efficiency section | 5 | Done | 2025-02-27 | 2025-03-04 | Teammate A | 5
Sprint 5 | T18 | Task | Content editing | 3 | Done | 2025-02-27 | 2025-03-02 | You | 3
Sprint 5 | T19 | Bug | Fix document errors | 2 | Done | 2025-02-28 | 2025-03-03 | Teammate B | 3
Sprint 5 | T20 | Story | Update driving guidelines | 8 | Done | 2025-03-01 | 2025-03-07 | You | 6
Sprint 6 | T21 | Story | Add safety updates | 8 | Done | 2025-03-13 | 2025-03-20 | Teammate A | 7
Sprint 6 | T22 | Task | Formatting and styling | 5 | Done | 2025-03-13 | 2025-03-18 | You | 5
Sprint 6 | T23 | Bug | Fix layout issues | 3 | Done | 2025-03-14 | 2025-03-19 | Teammate B | 5
Sprint 6 | T24 | Story | Update compliance section | 8 | Done | 2025-03-15 | 2025-03-22 | You | 7
Sprint 7 | T25 | Story | Revise maintenance section | 5 | Done | 2025-03-27 | 2025-04-02 | Teammate A | 6
Sprint 7 | T26 | Task | Content cleanup | 3 | Done | 2025-03-27 | 2025-03-30 | You | 3
Sprint 7 | T27 | Bug | Fix minor errors | 2 | Done | 2025-03-28 | 2025-04-01 | Teammate B | 4
Sprint 7 | T28 | Story | Update safety checklist | 8 | Done | 2025-03-29 | 2025-04-04 | You | 6
Sprint 8 | T29 | Story | Finalize handbook updates | 8 | Done | 2025-04-10 | 2025-04-15 | Teammate A | 5
Sprint 8 | T30 | Task | Final formatting | 5 | Done | 2025-04-10 | 2025-04-13 | You | 3
Sprint 8 | T31 | Bug | Fix final issues | 3 | Done | 2025-04-11 | 2025-04-14 | Teammate B | 3
Sprint 8 | T32 | Story | Review and approval | 8 | Done | 2025-04-12 | 2025-04-16 | You | 4