## Dashboard
Row Labels | Sum of Story Points
Sprint 1 | 13
Sprint 2 | 18
Sprint 3 | 19
Sprint 4 | 24
Sprint 5 | 18
Sprint 6 | 24
Sprint 7 | 18
Sprint 8 | 24
Grand Total | 158
Row Labels | Average of Cycle Time
Sprint 1 | 2.75
Sprint 2 | 4
Sprint 3 | 4.5
Sprint 4 | 5.75
Sprint 5 | 4.25
Sprint 6 | 6
Sprint 7 | 4.75
Sprint 8 | 3.75
Grand Total | 4.4688
Row Labels | Velocity | Average Velocity
Sprint 1 | 13 | 19.75
Sprint 2 | 18 | 37.875
Sprint 3 | 19 | 40.7143
Sprint 4 | 24 | 44.3333
Sprint 5 | 18 | 48.4
Sprint 6 | 24 | 56
Sprint 7 | 18 | 66.6667
Sprint 8 | 24 | 91
Grand Total | 158 | 158
Row Labels | Average of Cycle Time
Sprint 1 | 2.75
Sprint 2 | 4
Sprint 3 | 4.5
Sprint 4 | 5.75
Sprint 5 | 4.25
Sprint 6 | 6
Sprint 7 | 4.75
Sprint 8 | 3.75
Grand Total | 4.4688
Row Labels | Count of Task ID
Sprint 1 | 4
Sprint 2 | 4
Sprint 3 | 4
Sprint 4 | 4
Sprint 5 | 4
Sprint 6 | 4
Sprint 7 | 4
Sprint 8 | 4
(blank)
Grand Total | 32
Row Labels | Count of Task ID
Sprint 1 | 4
Sprint 2 | 4
Sprint 3 | 4
Sprint 4 | 4
Sprint 5 | 4
Sprint 6 | 4
Sprint 7 | 4
Sprint 8 | 4
Grand Total | 32

## Burndown -sprint 1
Day | Ideal -Pending work | Actual -Pending work | Completed Today
1 | 19 | 19 | 0
2 | 16 | 19 | 0
3 | 13 | 17 | 2
4 | 10 | 14 | 3
5 | 7 | 10 | 4
6 | 3 | 4 | 6
7 | 0 | 0 | 4

## Agile Performance Dashboard
Agile Sprint Performance Dashboard
Key Insights
Velocity varies due to task complexity differences
Cycle time shows workflow inconsistency
Throughput remains stable across sprints
Burndown shows late sprint completion trend
Sprint execution is stable but unevenly distributed
Recommedations
Standardize task sizing for consistent velocity based on complexity, risk and impact
Improve task breakdown to stabilize cycle time
Distribute workload evenly across sprint
Start working on tasks as soon as story is ready
Track progress mid-sprint to avoid end loading or include in daily scrum meeting

## Raw data
Sprint | Task ID | Issue Type | Summary | Story Points | Status | Start Date | End Date | Assignee | Cycle Time
Sprint 1 | T1 | Story | Update braking guidelines | 3 | Done | 2025-01-02 | 2025-01-04 | You | 2
Sprint 1 | T2 | Story | Revise safety section | 5 | Done | 2025-01-02 | 2025-01-06 | Teammate A | 4
Sprint 1 | T3 | Task | Format document layout | 2 | Done | 2025-01-03 | 2025-01-05 | You | 2
Sprint 1 | T4 | Bug | Fix content errors | 3 | Done | 2025-01-04 | 2025-01-07 | Teammate B | 3
Sprint 2 | T5 | Story | Update driver instructions | 5 | Done | 2025-01-16 | 2025-01-20 | You | 4
Sprint 2 | T6 | Story | Add new compliance rules | 8 | Done | 2025-01-16 | 2025-01-22 | Teammate A | 6
Sprint 2 | T7 | Task | Review formatting | 3 | Done | 2025-01-17 | 2025-01-21 | Teammate B | 4
Sprint 2 | T8 | Bug | Fix grammar issues | 2 | Done | 2025-01-18 | 2025-01-20 | You | 2
Sprint 3 | T9 | Story | Revise emergency procedures | 8 | Done | 2025-01-30 | 2025-02-05 | Teammate A | 6
Sprint 3 | T10 | Task | Content formatting | 3 | Done | 2025-01-30 | 2025-02-02 | You | 3
Sprint 3 | T11 | Story | Update safety visuals | 5 | Done | 2025-01-31 | 2025-02-06 | Teammate B | 6
Sprint 3 | T12 | Bug | Fix inconsistencies | 3 | Done | 2025-02-01 | 2025-02-04 | You | 3
Sprint 4 | T13 | Story | Add new regulations | 8 | Done | 2025-02-13 | 2025-02-20 | Teammate A | 7
Sprint 4 | T14 | Task | Review handbook draft | 5 | Done | 2025-02-13 | 2025-02-18 | You | 5
Sprint 4 | T15 | Bug | Fix formatting issues | 3 | Done | 2025-02-14 | 2025-02-19 | Teammate B | 5
Sprint 4 | T16 | Story | Update diagrams | 8 | Done | 2025-02-15 | 2025-02-21 | You | 6
Sprint 5 | T17 | Story | Revise fuel efficiency section | 5 | Done | 2025-02-27 | 2025-03-04 | Teammate A | 5
Sprint 5 | T18 | Task | Content editing | 3 | Done | 2025-02-27 | 2025-03-02 | You | 3
Sprint 5 | T19 | Bug | Fix document errors | 2 | Done | 2025-02-28 | 2025-03-03 | Teammate B | 3
Sprint 5 | T20 | Story | Update driving guidelines | 8 | Done | 2025-03-01 | 2025-03-07 | You | 6
Sprint 6 | T21 | Story | Add safety updates | 8 | Done | 2025-03-13 | 2025-03-20 | Teammate A | 7
Sprint 6 | T22 | Task | Formatting and styling | 5 | Done | 2025-03-13 | 2025-03-18 | You | 5
Sprint 6 | T23 | Bug | Fix layout issues | 3 | Done | 2025-03-14 | 2025-03-19 | Teammate B | 5
Sprint 6 | T24 | Story | Update compliance section | 8 | Done | 2025-03-15 | 2025-03-22 | You | 7
Sprint 7 | T25 | Story | Revise maintenance section | 5 | Done | 2025-03-27 | 2025-04-02 | Teammate A | 6
Sprint 7 | T26 | Task | Content cleanup | 3 | Done | 2025-03-27 | 2025-03-30 | You | 3
Sprint 7 | T27 | Bug | Fix minor errors | 2 | Done | 2025-03-28 | 2025-04-01 | Teammate B | 4
Sprint 7 | T28 | Story | Update safety checklist | 8 | Done | 2025-03-29 | 2025-04-04 | You | 6
Sprint 8 | T29 | Story | Finalize handbook updates | 8 | Done | 2025-04-10 | 2025-04-15 | Teammate A | 5
Sprint 8 | T30 | Task | Final formatting | 5 | Done | 2025-04-10 | 2025-04-13 | You | 3
Sprint 8 | T31 | Bug | Fix final issues | 3 | Done | 2025-04-11 | 2025-04-14 | Teammate B | 3
Sprint 8 | T32 | Story | Review and approval | 8 | Done | 2025-04-12 | 2025-04-16 | You | 4